## stories-35271257
FormattedID | ObjectID | Name | Status | BusinessValue | Iteration
US11106 | 35320802 | AVO Request Process (UI - Request) - I need to view current PTO and planned PTO balances | COMPLETED | 16 | Sprint 1
US11107 | 35320855 | AVO Request Process (UI - Request) - I need to request time off for one or more occurrences | COMPLETED | 16 | Sprint 1
US11108 | 35320908 | AVO Request Process (UI - Request) - I need to enter an AVO on behalf of an employee | COMPLETED | 16 | Sprint 1
US11111 | 35321212 | AVO Status Process (UI - My AVO) - I need to filter AVO (by status and date range) so that I can quickly view AVO of interest. | COMPLETED | 4 | Sprint 1
US11112 | 35321262 | AVO Status Process (UI - My AVO) - I need to view MY own AVOs | COMPLETED | 4 | Sprint 1
US11120 | 35322347 | AVO Approval Process (UI - Manage) - I need to assign alternate approvers | COMPLETED | 16 | Sprint 1
US11167 | 35370895 | Usability SP1 | COMPLETED | 0 | Sprint 1
US11114 | 35321376 | AVO Approval Process (UI - Manage) - I need to filter AVO (such as cost center, date range, status) so that I can quickly view AVO of interest. | COMPLETED | 16 | Sprint 2
US11115 | 35321472 | AVO Approval Process (UI - Manage) - I need to view all AVOs | COMPLETED | 16 | Sprint 2
US11117 | 35321820 | AVO Approval Process (UI - Manage) - I need to view employee AVO request info (such as current PTO balance, planned PTO) so that I can make informed decisions. | COMPLETED | 16 | Sprint 2
US11118 | 35321994 | AVO Approval Process (UI - Manage) - I need to approve and/or deny partial or all time off requests in AVO | COMPLETED | 16 | Sprint 2
US11123 | 35322869 | AVO Cancel Process (UI - My AVO) - I need to cancel an AVO which removes it from the AVO calendar | COMPLETED | 8 | Sprint 2
US11168 | 35370947 | Backlog Refinement SP1 | COMPLETED | 0 | Sprint 2
US11170 | 35371093 | Usability SP2 | COMPLETED | 0 | Sprint 2
US11171 | 35371265 | UI/QC/Tech Review SP1 | COMPLETED | 0 | Sprint 2
US11116 | 35321646 | AVO Approval Process (UI - Manage) - I need to view all approved AVO in calendar format and canceling an AVO removes it from the calendar | COMPLETED | 8 | Sprint 3
US11122 | 35322695 | AVO Approval Process (UI - Manage) - I need to view history of all AVO actions | COMPLETED | 8 | Sprint 3
US11172 | 35371437 | Backlog Refinement SP2 | COMPLETED | 0 | Sprint 3
US11173 | 35371867 | Usability SP3 | COMPLETED | 0 | Sprint 3
US11175 | 35372338 | UI/QC/Tech Review SP2 | COMPLETED | 0 | Sprint 3
US11174 | 35372042 | Backlog Refinement SP3 | COMPLETED | 0 | Sprint 4
US11176 | 35372771 | Usability SP4 | COMPLETED | 0 | Sprint 4
US11177 | 35372943 | UI/QC/Tech Review SP3 | COMPLETED | 0 | Sprint 4
US11127 | 35323565 | Discrepancy Resolution Process - I need to query discrepancies by cost center and date range | COMPLETED | 16 | Sprint 5
US11128 | 35323739 | Discrepancy Resolution Process - I need to view employee info: current PTO balance, planned PTO, AVOs so that I can make an informed decision | COMPLETED | 16 | Sprint 5
US11131 | 35324261 | Discrepancy Resolution Process - I need to clear discrepancies for an employee filtering on type of discrepancy | COMPLETED | 16 | Sprint 5
US11178 | 35373115 | Backlog Refinement SP4 | COMPLETED | 0 | Sprint 5
US11180 | 35373459 | UI/QC/Tech Review SP4 | COMPLETED | 0 | Sprint 5
US11182 | 35373803 | Usability SP5 | COMPLETED | 0 | Sprint 5
US11286 | 35635677 | Discrepancy Resolution Process - I need to clear multiple discrepancies for a cost center at one time, not forcing individual transactions | COMPLETED | 16 | Sprint 5
US11129 | 35323913 | Discrepancy Resolution Process - I need to view an individual's discrepancies in calendar filtering on types of discrepancies | IN_PROGRESS | 16 | Sprint 6
US11130 | 35324087 | Discrepancy Resolution Process - I need calendar to color code discrepancies and display more than one absence on single day so that I have an easy to read, complete visualization of discrepancies | IN_PROGRESS | 16 | Sprint 6
US11132 | 35324435 | Discrepancy Resolution Process - I need mass clearing up of discrepancies for an employee so that I can save time. | IN_PROGRESS | 16 | Sprint 6
US11134 | 35324783 | Discrepancy Resolution Process - I need to view number of dings auto calculated within rolling 60 working days so that I don't have to manually count them which is time consuming and error prone. | DEFINED | 16 | Sprint 6
US11137 | 35325305 | Discrepancy Resolution Process - Process data feeds to analyze and calculate discrepancies | IN_PROGRESS | 16 | Sprint 6
US11138 | 35325479 | Discrepancy Resolution Process - I need the ability to add discrepancies in the AMS tool in the event that PRISM is not providing that data to the application -- PERMISSIONS TBD | DEFINED | 32 | Sprint 6
US11181 | 35373631 | Backlog Refinement SP5 | DEFINED | 0 | Sprint 6
US11183 | 35374136 | Usability SP6 | NONE | 0 | Sprint 6
US11184 | 35374308 | UI/QC/Tech Review SP5 | DEFINED | 0 | Sprint 6
US11287 | 35659201 | Discrepancy Resolution Process - I need to issue disciplinary actions - NEED MORE INFO | DEFINED | 16 | Sprint 6
US11185 | 35374480 | Backlog Refinement SP6 | NONE | 0 | Sprint 7
US11186 | 35374652 | Usability SP7 | NONE | 0 | Sprint 7
US11187 | 35374824 | UI/QC/Tech Review SP6 | NONE | 0 | Sprint 7
US11188 | 35374996 | Backlog Refinement SP7 | NONE | 0 | Sprint 8
US11189 | 35375168 | Usability SP8 | NONE | 0 | Sprint 8
US11190 | 35375340 | UI/QC/Tech Review SP7 | NONE | 0 | Sprint 8
US11191 | 35375512 | Backlog Refinement SP8 | NONE | 0 | Sprint 9
US11192 | 35375684 | Usability SP9 | NONE | 0 | Sprint 9
US11193 | 35375856 | UI/QC/Tech Review SP8 | NONE | 0 | Sprint 9
US11194 | 35376028 | Backlog Refinement SP9 | NONE | 0 | Sprint 10
US11195 | 35376200 | Usability SP10 | NONE | 0 | Sprint 10
US11196 | 35376372 | UI/QC/Tech Review SP9 | NONE | 0 | Sprint 10
US11197 | 35376544 | Backlog Refinement SP10 | NONE | 0 | Sprint 11
US11198 | 35376716 | Usability SP11 | NONE | 0 | Sprint 11
US11199 | 35376888 | UI/QC/Tech Review SP10 | NONE | 0 | Sprint 11
US11200 | 35377060 | Backlog Refinement SP11 | NONE | 0 | Sprint 12
US11201 | 35377232 | Usability SP12 | NONE | 0 | Sprint 12
US11202 | 35377404 | UI/QC/Tech Review SP11 | NONE | 0 | Sprint 12
US11203 | 35377576 | Backlog Refinement SP12 | NONE | 0 | Sprint 13
US11204 | 35377748 | Usability SP13 | NONE | 0 | Sprint 13
US11205 | 35377920 | UI/QC/Tech Review SP12 | NONE | 0 | Sprint 13
US11206 | 35378092 | Backlog Refinement SP13 | NONE | 0 | Sprint 14
US11207 | 35378264 | Usability SP14 | NONE | 0 | Sprint 14
US11208 | 35378436 | UI/QC/Tech Review SP13 | NONE | 0 | Sprint 14
US11209 | 35378608 | Backlog Refinement SP14 | NONE | 0 | Sprint 15
US11210 | 35378780 | Usability SP15 | NONE | 0 | Sprint 15
US11211 | 35378952 | UI/QC/Tech Review SP14 | NONE | 0 | Sprint 15
US11212 | 35379124 | Backlog Refinement SP15 | NONE | 0 | Sprint 16
US11213 | 35379296 | Usability SP16 | NONE | 0 | Sprint 16
US11214 | 35379468 | UI/QC/Tech Review SP15 | NONE | 0 | Sprint 16
US11216 | 35379812 | Backlog Refinement SP16 | NONE | 0 | Sprint 17
US11217 | 35379984 | Usability SP17 | NONE | 0 | Sprint 17
US11218 | 35380156 | UI/QC/Tech Review SP16 | NONE | 0 | Sprint 17
US11219 | 35380328 | Backlog Refinement SP17 | NONE | 0 | Sprint 18
US11220 | 35380500 | Usability SP18 | NONE | 0 | Sprint 18
US11221 | 35380854 | UI/QC/Tech Review SP17 | NONE | 0 | Sprint 18
US11222 | 35381026 | Backlog Refinement SP18 | NONE | 0 | Sprint 19
US11223 | 35381198 | Usability SP19 | NONE | 0 | Sprint 19
US11224 | 35381370 | UI/QC/Tech Review SP18 | NONE | 0 | Sprint 19
US11095 | 35285545 | (Copy of) Setup Environment | COMPLETED | 0 | null
US11096 | 35286039 | (Copy of) Initiate Security Artifacts | COMPLETED | 0 | null
US11097 | 35286374 | (Copy of) Create Architecture Artifacts | COMPLETED | 0 | null
US11098 | 35286674 | (Copy of) Prepare and Present PO with Customer Facing Docs | COMPLETED | 0 | null
US11109 | 35320997 | nice to have - AVO Request Process (UI - Request) - I need to print AVO | DEFINED | 1 | null
US11113 | 35321327 | nice to have - AVO Status Process (UI - My AVO) - I need to print AVO | DEFINED | 1 | null
US11119 | 35322168 | removed 0n 11/16/16 - AVO Approval Process (UI - Manage) - I need to bump" requests based on seniority and floor availability" | DEFINED | 0 | null
US11121 | 35322521 | nice to have - AVO Approval Process (UI - Manage) - I need to print AVO | DEFINED | 1 | null
US11124 | 35323043 | ACS Call-In Process - I need to view and hear the called in absences from the ACS | DEFINED | 16 | null
US11125 | 35323217 | ACS Call-In Process - I need to make selections via voice recognition so that I don't have to use the phone keypad which could be dangerous when driving | DEFINED | 16 | null
US11126 | 35323391 | ACS Call-In Process - I need to receive broadcast message to pull over if I am driving prior to using the system as a safety reminder | DEFINED | 16 | null
US11133 | 35324609 | Discrepancy Resolution Process - I need to adjust modified work schedule for factories to decrease the number of incorrectly identified discrepancies so that I can save time by not having to resolve these - NEED MORE INFO. | DEFINED | 16 | null
US11135 | 35324957 | Discrepancy Resolution Process - I need to view employee's status in step back process" auto calculated based on the number of disciplinary actions with a predefined timeframe." | DEFINED | 16 | null
US11136 | 35325131 | nice to have - Discrepancy Resolution Process - I need to print the step back" status so that I can attach it for delivery in the event that recipients don't have access to computer." | DEFINED | 1 | null
US11139 | 35325653 | Discrepancy Resolution Process - I need the ability to make corrections such as no PTO/FMLA" to "FMLA" has been approved - NEED MORE INFO" | DEFINED | 32 | null
US11140 | 35325827 | Reports - I need to create Ad hoc/customizable reports with templates can be saved for future use (SOLR) | DEFINED | 8 | null
US11141 | 35326001 | Reports - I need to export all reports | DEFINED | 16 | null
US11142 | 35326175 | Reports - I need to view open discrepancies that require supervisor action so they can be addressed in a timely manner per Union rules; Supervisor Discrepancies | DEFINED | 8 | null
US11143 | 35326349 | Reports - I need to view Pre-Planned Absence Reports (AVO) to assist with manpower planning. | DEFINED | 8 | null
US11144 | 35326523 | Reports - I need to view Employee Attendance filter by date range (such as 30, 60, 1 year) for historical comparision and trends. | DEFINED | 8 | null
US11145 | 35326697 | Reports - I need to view Occupation Cost Center by Seniority for manpower planning. | DEFINED | 8 | null
US11146 | 35326871 | Reports - I need to view Scheduled Start Times for employees for troubleshooting purposes to assist with common discrepancy of Prism not being updated with employee's new schedule. | DEFINED | 8 | null
US11147 | 35327045 | Reports - ACS Call Volume and ACS Custom Call Volume - TBD | DEFINED | 8 | null
US11148 | 35327219 | Admin - I need to maintain look up values to support the application. | DEFINED | 16 | null
US11149 | 35327393 | Admin - I need to maintain user access so that information is limited to the correct audience. | DEFINED | 16 | null
US11150 | 35327574 | Data Integration - receive updates from SPEED on a daily basis to note when disciplinary actions have been removed | DEFINED | 8 | null
US11151 | 35327748 | Data Integration - receive updates from SPEED on a daily basis to see all disciplinary actions for an employee | DEFINED | 8 | null
US11152 | 35327922 | removed on 11/16/16 - Data Integration - Updates made to PRISM timecards should automatically be posted to AMS calendar | DEFINED | 0 | null
US11153 | 35328096 | Data Integration - Receive discrepancy data for Sat and Sun since those are working days for some employees | DEFINED | 8 | null
US11154 | 35328270 | Data Integration - Receive from PRISM holiday hours tagged as such eliminating it from showing up as discrepancy | DEFINED | 8 | null
US11155 | 35328444 | Notifications - FIRST NOTICE receive notifications of any un-cleared discrepancies on a weekly basis | DEFINED | 8 | null
US11156 | 35328618 | Notifications - SECOND NOTICE receive notifications of any un-cleared discrepancies on a weekly basis | DEFINED | 8 | null
US11157 | 35328792 | Notifications - THIRD NOTICE receive notifications of any un-cleared discrepancies on a weekly basis | DEFINED | 8 | null
US11158 | 35328966 | Notifications - FOURTH receive notifications of any un-cleared discrepancies on a weekly basis | DEFINED | 8 | null
US11159 | 35329140 | nice to have - Notifications - I want to manage my preferences for receiving notifications (e.g. frequency, email, dashboard, etc.) | DEFINED | 1 | null
US11160 | 35336071 | nice to have - Notifications - I need to receive notification when an AVO request has been submitted, with the option to opt out of these emails | DEFINED | 1 | null
US11161 | 35336245 | Notifications - I need to receive notification when an employee adds an absence to the Automated Call-In System, with the option to opt out of these emails | DEFINED | 8 | null
US11162 | 35336419 | Notifications - I need to receive notification when my AVO request is approved or denied, | DEFINED | 16 | null
US11163 | 35336593 | nice to have - Notifications - I need to receive notification when an AVO is cancelled, with the option to opt out of these emails | DEFINED | 1 | null
US11164 | 35336767 | Notifications - I need to be able to send out email notifications | DEFINED | 8 | null
US11165 | 35336941 | Reports - I need to view Employee or Department Absence to assist with manpower planning and to answer how discrepancies are being answered; already esiting application as multiple reports. | DEFINED | 8 | null
US11250 | 35554151 | ACS Call-In Process - ACS / IVR Service Integration | DEFINED | 8 | null
US11260 | 35588346 | Discrepancy Resolution Process - I need to view employee info: disciplinary steps so that I can make an informed decision | DEFINED | 16 | null
US11261 | 35588846 | Discrepancy Resolution Process - I need to view employee info: ACS calls so that I can make an informed decision | DEFINED | 16 | null
US11269 | 35603106 | ACS Call-In Process - ACS/IVR Service Integration (Architecture Requirement) | DEFINED | 8 | null

## Sheet1
Sprint | SumBV | Cumulative_SumBV | % Projected | SumBVCompleted | Cumulative_SumBVCompleted | % completed (all) | % completed (assigned) | MovingAverage/Forecast
Sprint 1 | 72 | 72 | 9.904% | 72 | 72 | 9.904% | 20.45%
Sprint 2 | 72 | 144 | 19.81% | 72 | 144 | 19.81% | 40.91% | 125.3333
Sprint 3 | 16 | 160 | 22.01% | 16 | 160 | 22.01% | 45.45% | 154.6667 | 29.3333
Sprint 4 | 0 | 160 | 22.01% | 0 | 160 | 22.01% | 45.45% | 176 | 21.3333
Sprint 5 | 64 | 224 | 30.81% | 48 | 208 | 28.61% | 59.09% | 184 | 8
Sprint 6 | 128 | 352 | 48.42% | 0 |  |  |  | 208 | 24 | 20.6667 | Mean Delta
Sprint 7 | 0 | 352 | 48.42% | 0 |  |  |  | 228.6667
Sprint 8 | 0 | 352 | 48.42% | 0 |  |  |  | 249.3333
Sprint 9 | 0 | 352 | 48.42% | 0 |  |  |  | 270 |  | 37.14%
Sprint 10 | 0 | 352 | 48.42% | 0 |  |  |  | 290.6667 |  | 39.98%
Sprint 11 | 0 | 352 | 48.42% | 0 |  |  |  | 311.3333 |  | 42.82%
Sprint 12 | 0 | 352 | 48.42% | 0 |  |  |  | 332 |  | 45.67%
Sprint 13 | 0 | 352 | 48.42% | 0 |  |  |  | 352.6667 |  | 48.51%
Sprint 14 | 0 | 352 | 48.42% | 0 |  |  |  | 373.3333 |  | 51.35%
Sprint 15 | 0 | 352 | 48.42% | 0 |  |  |  | 394 |  | 54.2%
Sprint 16 | 0 | 352 | 48.42% | 0 |  |  |  | 414.6667 |  | 57.04%
Sprint 17 | 0 | 352 | 48.42% | 0 |  |  |  | 435.3333 |  | 59.88%
Sprint 18 | 0 | 352 | 48.42% | 0 |  |  |  | 456 |  | 62.72%
Sprint 19 | 0 | 352 | 48.42% | 0 |  |  |  | 476.6667 |  | 65.57%
null | 375 | 727 | 100% | 0 |  |  |  | 497.3333 |  | 68.41%
[8 empty] | 518 | Sprint 20 | 71.25%
[8 empty] | 538.6667 | Sprint 21 | 74.09%
[8 empty] | 559.3333 | Sprint 22 | 76.94%
[8 empty] | 580 | Sprint 23 | 79.78%
[8 empty] | 600.6667 | Sprint 24 | 82.62%
[8 empty] | 621.3333 | Sprint 25 | 85.47%
[8 empty] | 642 | Sprint 26 | 88.31%
[8 empty] | 662.6667 | Sprint 27 | 91.15%
[8 empty] | 683.3333 | Sprint 28 | 93.99%
[8 empty] | 704 | Sprint 29 | 96.84%
[8 empty] | 724.6667 | Sprint 30 | 99.68%